## Week 1
Sprint Name: | Week 1
Goal: | Create a working command line application (CLI) that supports CRUD operations for an Bank Management Sytem(BMS) using Core Java.
Tasks:
Task 1 | Describe the project architecture with UML Structural and Behavioural diagrams.
Status: | TODO
SubTask 1 | Create the Use Case Diagram of Bank Management System
SubTask 2 | Create Activity Diagrams of the system
a) Customer Login
b) Account Registration
c) Withdraw Funds
d) Deposit Funds
e) Intra Bank Funds Transfer
SubTask 3 | Create BMS Class Diagram
SubTask 4 | Create Sequence Diagrams of :
a) Customer Login
b) Account Registration
c) Withdraw Funds
d) Deposit Funds
e) Intra Bank Funds Transfer
Done: | UML model project uploaded to Git repo in pdf format.
Task 2 | Create a Maven project in IntelliJ.
Status: | TODO
SubTask 1 | Write up the dependencies in the pom.xml for a Java application.
SubTask 2 | Include the JUnit5 dependency.
SubTask 3 | Add JaCoCo Maven Plug-in for code coverage.
Done: | Scaffold project in IntelliJ workspace.
Task 3 | Implement the Java application using the TDD approach.
Status: | TODO
SubTask 1 | Write the initial test cases using JUnit5. Use Mockito to mock the database.
SubTask 2 | Create the java classes according to the UML model defined along with the associated methods for JDBC operations.
Done: | Passing JUnit test cases
Task 4 | Create the Database schema and connect to it with JDBC.
Status: | TODO
SubTask 1 | Create the database tables, constraints and relationships between tables.
SubTask 2 | Load sample data in to the database
SubTask 3 | Connect to the database using JDBC
SubTask 4 | Create the Command Line interface with the Scanner class to retrieve user input and display the results.
Done: | A working CLI application according to specifications.
Task 5 | BDD Using Cucumber
Status: | TODO
SubTask 1 | Use behavior-driven development (BDD) to define clear, unambiguous requirements
SubTask 2 | Turn these requirements into automated acceptance tests.
Done: | Verification of application’s behavior
Documentation of each feature
Task 6 | Check Project artifacts and code into BitBucket
Status: | TODO
SubTask 1 | Push the code base to the appropriate Bitbucket repository
Done: | Project artifacts and code available and upto date in the repository.

## Week 2
Sprint Name: | Week 2
Goal: | Enhance the CLI application with user friendly error messages
Tasks:
Task 1 | Upgrade the Maven project to factor in error handling and DAO classes
Status: | TODO
SubTask 1 | Follow the TDD approach to refactoring the application to include exception handling for each CRUD operation. Create a custom exception class to handle business logic errors.
SubTask 2 | Create classes and interfaces for the Login, Registration and each Funds Transfer module.
SubTask 3 | Create a DAO class and interface for each module - Login, Registration and each Funds Transfer module.
SubTask 4 | Implement Login, Registration and each Funds Transfer module classes to use the corresponding DAO to perform CRUD operations
Done: | Upgraded working CLI application.
Task 2 | BDD Using Cucumber
Status: | TODO
SubTask 1 | Use behavior-driven development (BDD) to define clear, unambiguous requirements
SubTask 2 | Turn these requirements into automated acceptance tests.
Done: | Verification of application’s behavior
Documentation of each feature
Task 3 | Update Architecture Diagrams
Status: | TODO
SubTask 1 | Changes to the code base needs to be reflected in the UML class and sequence diagrams.
Done: | Updated project documentation
Task 5 | Check Project artifacts and code into BitBucket
Status: | TODO
SubTask 1 | Push the code base to the appropriate Bitbucket repository
Done: | Project artifacts and code available and upto date in the repository.

## Week 3
Sprint Name: | Week 3
Goal: | Introduce JPA with Hibernate and REST APIs for CRUD operations
Tasks:
Task 1 | Update the Maven pom
Status: | TODO
SubTask 1 | Add the JPA and Hibernate dependencies.
SubTask 2 | Remove the JDBC dependencies.
Done: | Project configured for JPA with Hibernate.
Task 2 | Create REST APIs for the CRUD operations.
Status: | TODO
SubTask 1 | Use JAX-RS to create the REST APIs for CRUD operations.
SubTask 2 | Test the APIs in Postman.
Done: | REST APIs tested successfully in Postman.
Task 3 | Refactor to use JPA with Hibernate for database operations
Status: | TODO
SubTask 1 | Follow the TDD approach to refactoring the application to use JPA with Hibernate instead of JDBC.
SubTask 2 | Write the JUnit test cases for the refactored Java classes.
SubTask 3 | Use @Spy to mock the database implementation class.
SubTask 4 | Implement the refactored classes according to specifications.
Done: | Application successfully connects to the database.
Application satisfies Testing requirements(Unit and BDD) in the Conceptual Problem Statement.
Task 4 | Create a Performance Test Plan in JMeter
Status: | TODO
SubTask 1 | Do a performance analysis of the application for 3000 users. Check that the system satisfies the NFRs and SLAs in the Conceptual Problem Statement.
Done: | JMeter shows the test result in Graph format.
Task 5 | Update Architecture Diagrams
Status: | TODO
SubTask 1 | Changes to the code base needs to be reflected in the UML class and sequence diagrams.
Done: | Updated project documentation
Task 6 | Check Project artifacts and code into BitBucket
Status: | TODO
SubTask 1 | Push the code base to the appropriate Bitbucket repository
Done: | Project artifacts and code available and upto date in the repository.

## Week 4
Sprint Name: | Week 4
Goal: | Create the backend tier for the BMS using Spring Boot with REST and Data JPA
Tasks:
Task 1 | Update the Maven pom
Status: | TODO
SubTask 1 | Add the dependencies for Spring MVC, Data JPA, Bean Validator Reference Implementation and Database Connector.
SubTask 2 | Remove the JPA and Hibernate dependencies.
SubTask 3 | (Optional) You may add other dependencies like Lombok to ease the burden of writing boilerplate code.
Done: | Project configured for Spring MVC with REST and Data JPA.
Task 2 | Create the REST Endpoints for the CRUD operations
Status: | TODO
SubTask 1 | Follow the TDD approach to creating the back end tier. You will still be writing the test cases using JUnit but using the framework support in Spring Boot. You need to cover unit tests that can run in isolation as well as integration tests that will bootstrap Spring context before executing tests.
SubTask 2 | The following classes of tests need to be implemented:- a)Smoke and Sanity test:-. Check if the Spring Context is running. b)System test:- It will test the complete application. c)Integration test:- Test the Controller tier together with the Service layer. d)JPA test:- Test the Service tier and the database.
SubTask 3 | Create the Controller, Service and Repository tiers.
SubTask 4 | Create RESTful Web Service endpoints corresponding to each CRUD operation in the Controller tier.
SubTask 5 | Use Status Codes in Error Handling
SubTask 6 | Implement global exception handling with @ControllerAdvice for Controller classes.
SubTask 7 | Use the JSR 380 and implement Validation on the model objects.
Done: | Successfully test the REST API endpoints in Postman.
Task 3 | Create a Pipeline project in Jenkins to automate the workflow
Status: | TODO
SubTask 1 | Create a Jenkins Pipeline project
SubTask 2 | Checkout/clone the code base from GitHub repo
SubTask 3 | Compile and package the application
SubTask 4 | Run the JUnit tests and publish the results
SubTask 5 | Add a stage to the pipeline to deploy the application to Tomcat server.
SubTask 6 | Add a stage to the pipeline to do a Performance Test with Jmeter and publish the results.
SubTask 6 | Add a stage to the pipeline to run the Cucumber BDD tests and publish the results
Add a stage to the pipeline to integrate SonarQube with Jenkins.
Done: | Build executed successfully in Jenkins with passing test cases
Application deployed successfully to Tomcat server.
Unit and BDD test reports available in Jenkins and SonarQube
System satisfies the NFRs and SLAs in the Conceptual Problem Statement as well as the Testing requirements.
Task 4 | Update Architecture Diagrams
Status: | TODO
SubTask 1 | Changes to the code base needs to be reflected in the UML class and sequence diagrams.
Done: | Updated project documentation
Task 5 | Check Project artifacts and code into BitBucket
Status: | TODO
SubTask 1 | Push the code base to the appropriate Bitbucket repository
Done: | Project artifacts and code available and upto date in the repository.

## Week 5
Sprint Name: | Week 5
Goal: | Create the Frontend for the BMS using React and Dockerize the application. Deploy the Spring Boot and ReactJs app to Amazon Web Services.
Tasks:
Task 1 | Create a React Project in Visual Studio Code
Status: | TODO
SubTask 1 | Follow TDD with Jest to build the complete the front end using React, HTML5 and CSS3. Structure your React application according to the Atomic Design Pattern: atoms > molecules > organisms > templates > pages
SubTask 2 | Consume the REST APIs in the Spring Boot-REST-Data JPA back end from your React application using AXIOS.
SubTask 3 | The following screens need to be developed: a) Login Page for Bank Customer c) Dashboard Page - displayed after login. Should display cuurent bank balance. d) View Statement Page g) Withdraw Funds Page h) Deposit Funds Page i) Logout Functionality
SubTask 4 | Introduce a 3 second delay into the application when the list of records is being retrieved, or when a record is being updated or added.
SubTask 5 | The pages displaying the list of records and save/update of a record should show a Spinner or Progress Bar while the page is being displayed or the records are being retrieved. The Spinner or Progress Bar should disappear when the page is rendered.
SubTask 6 | The page(s) where a record is added or updated should have the Save/Update button disabled while a new record is being saved or updated. The label on the button should change from 'Save' to 'Saving..'.
SubTask 7 | On successful save or update, the user should only then be navigated to the list of records.
SubTask 8 | On unsuccessful save or update, the user should remain on the page. An notification should be displayed with a user friendly error message.
SubTask 9 | On Delete, the user must immediately be navigated to the list of records(Optimistic Deletes) unless the Delete buttons are on the same page; in which case the page simply needs to be reloaded to display the updated list.
SubTask 10 | The notification for an unsuccessful Create,Update or Delete action will not have a display interval. It will need to be manually closed by the end user.
SubTask 11 | Use Toast Notifications or SweetAlert or any library of your choosing to display alerts and messages to a user. It can be a success message, warning message, or custom message. You may set the display interval to 2-3 seconds.
SubTask 12 | Develop the production server of your react app with Node.js
Done: | Full featured working application deployed with an Express.js server.
Task 2 | Create the Dockerfile environments
Status: | TODO
SubTask 1 | Create the Dockerfile for the Spring Boot app.
SubTask 2 | Create the Dockerfile for the ReactJS app.
Done: | Dockerfiles created for the Spring Boot and ReactJs apps.
Task 3 | Provision an Amazon RDS PostgreSQL database
Status: | TODO
SubTask 1 | Use your AWS account to provision a PostgreSQL RDS for the Spring Boot back end.
SubTask 2 | Connect to the RDS from your local and load sample data.
Done: | Amazon RDS PostgreSQL database configured and ready to accept a connection from the Spring Boot app.
Task 4 | Create the Jenkins Pipeline for ReactJs app
Status: | TODO
SubTask 1 | Follow the steps outlined in Week 4 - Task 3 to create the Jenkins Pipeline for the React JS app.
SubTask 2 | Add a stage to the pipeline to deploy the contents of the "build" folder to Amazon S3 bucket.
Done: | index.html shoul render when hitting the AWS S3 URL
Task 5 | Update the Jenkins Pipeline for Spring Boot App
Status: | TODO
SubTask 1 | Add stages to the pipeline created in Week 4 - Task 3 to build a Docker image and push it to Docker Hub.
SubTask 2 | Add a stage to the pipeline to start/restart an AWS EC2 instance.
SubTask 3 | Write a startup script for the EC2 instance which will pull the latest image of the Spring Boot app from DockerHub and install it in EC2.
Done: | ReactJS app connects to Spring Boot app in AWS.
Task 6 | BDD Using Cucumber
Status: | TODO
SubTask 1 | Use behavior-driven development (BDD) to define clear, unambiguous requirements
SubTask 2 | Turn these requirements into automated acceptance tests.
Done: | Verification of application’s behavior
Documentation of each feature
Task 7 | Update Architecture Diagrams
Status: | TODO
SubTask 1 | Changes to the code base needs to be reflected in the UML class and sequence diagrams.
Done: | Updated project documentation
Task 8 | Check Project artifacts and code into BitBucket
Status: | TODO
SubTask 1 | Push the code base to the appropriate Bitbucket repository
Done: | Project artifacts and code available and upto date in the repository.